## Sheet1
Task |  | Assigned To | Completed By
Java ( BackEnd )
| Game.java | Alok Jha | Alok Jha
| App.java | Alok Jha | Alok Jha
| Chat.java | Alok Jha | Alok Jha
| HttpServer.java | Alok Jha | Alok Jha
| Player.java | Alok Jha | Alok Jha
HTML, CSS and JS ( Front End )
| index.html | Alok Jha, Ujjwal Sood | Alok Jha, Ujjwal Sood
| All other CSS file | David Akinmade, Ujjwal Sood, Alok Jha | David Akinmade, Ujjwal Sood, Alok Jha
| websocket.js | Alok Jha | Alok Jha
| navigation.js | Alok Jha | Alok Jha, Ujjwal Sood
Deployment | Deploy to cse3310.org site | Alok Jha | Alok Jha
Foul word removement | words.txt | Ravi Ray | Ravi Ray
Unit Test | AppTest.java | Daniel Bonta,Saad Khairullah | Daniel Bonta,Saad Khairullah
Requirement Spreadsheet | Verify and write requirements | Daniel Bonta, Alok Jha | All